## Sheet1
Activity # | Activity Name | Activity Name Description | Number of Days | Start Date | Dependencies | Milestone
1 | Management | Project Management | 20 | 2016-01-12
1.1 | Issue of Data Corruption |  | 12 | 2016-01-12
1.2 | Schedule of task |  | 8 | 2016-01-25
2 | Research | Research documentation | 63 | 2016-02-01
2.1 | Gather information |  | 20 | 2016-02-01
2.2 | Create document |  | 42 | 2016-02-26
3 | Design | System Architecture | 75 | 2016-04-04
3.1 | Collect Requirements |  | 14 | 2016-04-04
3.2 | Create system design |  | 30 | 2016-06-06
3.3 | Develop system design proposal |  | 3 | 2016-07-11
4 | Build | System Development | 78 | 2016-07-14
4.1 | Complete all coding requirement |  | 58 | 2016-07-14
4.2 | Detailed testing plan |  | 3 | 2016-09-26
4.3 | Include all content |  | 10 | 2016-09-29
4.4 | Testing |  | 10 | 2016-10-14
5 | Implementation | Transfer System to flash drive | 30 | 2016-10-27
5.1 | Redesign software |  | 20 | 2016-11-23
5.2 | Embed in Flash Drive |  | 15 | 2016-12-03
6 | Training | Provide user training | 4 | 2016-12-09
7 | Project Handoff/ Closure | Finalizing Whole Project | 3 | 2016-12-12
| TOTAL DAYS |  | 273