## Sheet1
Activity # | Activity Name | Activity Name Description | # of Days | Start Date | Dependency | Milestone
1 | Management | Project Management | 21 | 2016-01-12
1.1 | How to solve the issue of Data Corruption |  | 12 | 2016-01-12
1.1.1 | Research about DC |  | 7 | 2016-01-12
1.1.2 | Educate themselves |  | 5 | 2016-01-19
1.2 | Create a schedule of task |  | 8 | 2016-01-22
1.2.1 | Presented through a WBS |  | 2 | 2016-09-26
1.2.2 | Presented though a table |  | 2 | 2016-09-29
1.2.3 | Presented through other visual presentation |  | 4 | 2016-10-03
1.3 | Present the plan |  | 1 | 2016-10-07
1.3.1 | Approval of Adviser |  | 1 | 2016-10-07
2 | Research | Research documentation | 63 | 2016-01-12
2.1 | Gather information |  | 20 | 2016-01-19
2.1.1 | Interview adviser |  | 1 | 2016-01-23
2.2 | Create document |  | 42 | 2016-01-26
2.2.1 | Create project context |  | 14
2.2.2 | Create purpose & description |  | 7
2.2.3 | Create scope & limitation |  | 7
2.2.4 | Create related studies |  | 14
2.3 | Present document |  | 1 | 2016-04-15
2.3.1 | Present to adviser |  | 1 | 2016-04-15
3 | Design | System Architecture | 25 | 2016-06-13 |  | Detailed Design
3.1 | Collect Requirements |  | 7 | 2016-06-13
3.2 | Create system design |  | 14 | 2016-06-20
3.3 | Develop system design proposal |  | 3 | 2016-07-08
3.3.1 | Review and approval for panel |  | 3 | 2016-07-08
3.4 | Report to adviser |  | 1 | 2016-07-12
4 | Build | System Development | 88 | 2016-07-15 |  | Software Code
4.1 | Complete all coding requirement |  | 54 | 2016-07-19
4.1.1 | Approve system design |  | 1
4.2 | Provide detailed testing plan for adviser |  | 3
4.3 | Include all content |  | 10
4.3.1 | Provide redesign software by adviser |  | 5
4.4 | Testing | Testing system | 20 | 2016-11-07
4.4.1 | Resolve any coding |  | 10 | 2016-11-07
4.4.2 | System issues |  | 10 | 2016-11-12
4.5 | Report to adviser |  | 1 | 2016-11-15
5 | Implementation | Transfer System to flash drive | 15 | 2016-11-17
5.1 | Implement newly redesign software |  | 14 | 2016-11-17
5.1.1 | External Storage Device/Flash Drive |  | 14
5.2 | Report to adviser |  | 1 | 2016-12-07
6 | Training | Provide user training | 4 | 2016-12-05 |  | Training Certificate
6.1 | Provide training |  | 3 | 2016-12-05
6.1.1 | Approve training plan |  | 1 | 2016-12-07
6.2 | Report to adviser |  | 1 | 2016-12-07
7 | Project Handoff/ Closure | Finalizing system | 9 | 2016-12-11
7.1 | Provide all document by adviser |  | 2
7.1.1 | Approved project plan |  | 1
7.2 | Present project closure to adviser |  | 1
7.2.1 | Review and approval of adviser |  | 1
7.3 | Completion of project requirements |  | 5
7.3.1 | Provided checklist for all complete task |  | 5
7.4 | Report to adviser |  | 1
Total of Days |  |  | 225